{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["云南保山电力股份有限公司2024年8月35kV及以上综合停电计"],"read":"whole","date_system":"1900"}

{"sheet":"云南保山电力股份有限公司2024年8月35kV及以上综合停电计","index":0,"n_rows":23,"n_cols":8,"rows_kept":23,"merged":[[0,0,0,7],[2,0,2,7],[3,0,4,0],[3,2,4,2],[3,3,4,3],[3,5,4,5],[3,6,4,6],[3,7,4,7],[5,0,6,0],[5,2,6,2],[5,3,6,3],[5,5,6,5],[5,6,6,6],[5,7,6,7],[7,0,8,0],[7,2,8,2],[7,3,8,3],[7,5,8,5],[7,6,8,6],[7,7,8,7],[9,0,10,0],[9,2,10,2],[9,3,10,3],[9,4,10,4],[9,5,10,5],[9,6,10,6],[9,7,10,7],[11,0,11,7],[12,0,14,0],[12,2,14,2],[12,3,14,3],[12,4,14,4],[12,5,14,5],[12,6,14,6],[12,7,14,7],[15,0,15,7],[16,0,17,0],[16,2,17,2],[16,3,17,3],[16,4,17,4],[16,5,17,5],[16,6,17,6],[16,7,17,7],[18,0,19,0],[18,2,19,2],[18,3,19,3],[18,4,19,4],[18,5,19,5],[18,6,19,6],[18,7,19,7],[21,0,21,7]]}
["云南保山电力股份有限公司2024年8月35kV及以上综合停电计划表"]
["序号","变电站","停设备电压等级","停电设备名称","工作内容","调整后开工日期","调整后完工日期","停电时长"]
["永昌"]
[1,"110kV西邑变","35kV","西羊线","变修所：同步开展定检预试工作；线路：20号耐张塔A相大号侧，B相小号侧破损瓷瓶更换","8月1日12:00","8月1日15:00",3]
[null,"35kV羊邑变",null,null,"变修所：同步开展定检预试工作"]
[2,"110kV辛街变","35kV","辛东线","线路：12号直线双杆大号侧中相防震锤复位；22号直线塔大号侧下边线防震复位。变修：同步开展定检","8月2日12:00","8月2日16:00",4]
[null,"35kV东门变",null,null,"变修所：同步开展定检预试工作"]
[3,"110kV辛街变","110kV","辛长线","变修：断路器定检预试及保护装置保护检验","8月6日09:00","8月6日17:00",8]
[null,"110kV长岭岗变",null,null,"/"]
[4,"110kV柯街变","110kV","柯西线","8月1日永昌线路：跟换绝缘子。8月5日永昌变电：预试定检。两项工作与昌宁#5杆迁改同步开展。","8月1日永昌线路；8月5日永昌变修","8月1日永昌线路；8月5日永昌变修",24]
[null,"110kV西邑变"]
["施甸"]
[1,"110kV辛街变","110kV","辛七邱线","施甸线路：更换绝缘子：N10塔C相小号侧绝缘子破损1片；N11塔A相绝缘子破损1片；N12塔A相大号侧绝缘子破损1片。变修、电厂无工作","8月6日20:00","8月6日22：30",2.5]
[null,"110kV七〇七变"]
[null,"邱家寨光伏升压站"]
["昌宁"]
[1,"松子山风电厂","110kV","松柯线","电厂：110kV松柯线年度定检及避雷器加装，35kV集电线路年度定检预试、终端塔电缆屏蔽线试验、风机终端塔架空避雷线检查、复合支柱绝缘子检测、避雷器引流线更换。","8月18日08:30","8月21日23:00",87]
[null,"110kV柯街变"]
[2,"110kV柯街变","110kV","柯西线","昌宁线路：#5杆迁改。永昌线路：跟换绝缘子。永昌变电：预试定检","8月1日08:00","8月7日20:00",180]
[null,"110kV西邑变"]
[3,"35kV珠街变","35kV","母线","珠街光伏35kV并网线路间隔接入及调试","2024-08-10","2024-08-10","/"]
["龙陵"]
[1,"35kV河头变","35kV","母线","基建：新增主变间隔搭接。主变吊装，电容器组吊装，电容器柜组装。变修：35kV间隔隔离开关闭锁调整；10kV3条负荷出线检修消缺","8月29日08:00","8月29日14:00",6]